## Model 4.1
Item Description | Dimensions | Cost £s | Link | .
6.5HP OHV Engine | 36 x 31 x 24cm | 72.69 | https://www.amazon.co.uk/Ejoyous-Replacement-Industrial-Agricultural-Air-Cooled/dp/B08VDQGQ27/ref=sr_1_5?dib=eyJ2IjoiMSJ9.fcwco9gx_NJeJrqLN_ejJzktR_G-f0qoU3bGH5i9seVFZ2ste6iZGOQTx0Kjy0fnp64jkD8NZ9BZYrDXaNFVswHK_SJmlRScM4KSGqjKaDH-RXHidWqfCMvH9spU7W1Wa82TKVmsNO3S7-BuGQSQTiz1z5uF4DjBWriEAHqPft_PSOCFWipIKsYUSNImD_-fxaG1iT9_Jrm3ZeMu9bc9Gp-bEIwLMKm4hAL-jIzWClI.QcyiH1B1XjjBzNuCx__dSvYZZBt-Ws969OAY2AzWnCg&dib_tag=se&keywords=6.5hp+engine&qid=1738700015&sr=8-5 | .
4x Wheels (After axle comes) | 25 x 7.5cm | 23.95 | https://www.amazon.co.uk/ZENO-Pneumatic-Wheelbarrow-Puncture-Replacement/dp/B0BBKXVZ4G/ref=sr_1_13_sspa?dib=eyJ2IjoiMSJ9.A3OOQI0_Zv-fo18qNzdqTmxP0r7wTFkRvhcTcSbwpBPvszur4SN1Q1apeLngrmvNcu7vUdwZsfugdFv7DMdo0gQuJxI1moLNRtHKMiri1hJS8MKFt2gp3L2R-5zekSb64ot14EGvSoIcmMjte0-bVNUt3yluLnT4ugRRzaeIkIhBUhFCJxYDYiLwd4JzYhxImPQ62vt91eZbMvs-I_U_wkl9rSDSAmiqyqgltgCXHRCB4m1mOrIih7_bnp8GJE8pVP_V2P79LMwAditg-lQFbkpDm9P-PYybokWQ2w34w_U.NpfzG7XFxJUR7-twmqepLcpjDf4bwQytvQa2rpCzBUE&dib_tag=se&keywords=go+kart+wheels&qid=1728220361&s=automotive&sr=1-13-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9tdGY&psc=1 | https://www.amazon.co.uk/dp/B0DJQRMKHH/ref=sspa_dk_detail_0?psc=1&pd_rd_i=B0DJQRMKHH&pd_rd_w=MmJJW&content-id=amzn1.sym.46187d6a-4306-4bc6-830c-7b2085e0e39f&pf_rd_p=46187d6a-4306-4bc6-830c-7b2085e0e39f&pf_rd_r=ZZVB4FYTXGAYA5ZTEK21&pd_rd_wg=yVqgD&pd_rd_r=18384dd0-1d6e-486c-ad9b-7e99c9ac4b8c&s=automotive&sp_csd=d2lkZ2V0TmFtZT1zcF9kZXRhaWw
Torque Converter kit |  | 37.42 | https://www.ebay.co.uk/itm/204669662830 | .
Rear Axle Kit +Brake | 810mm | 105.2 | https://www.amazon.co.uk/GXYWADY-Master-Cylinder-Replacement-Rebuild/dp/B0CH3CTZ4F/ref=sr_1_1?dib=eyJ2IjoiMSJ9.6JNiA91wPg11dpNu-uDXeXTu5H9Q8Hbqk42hSsmj9G-tYq6BM_3skaf8Lt_zgGMKdZXPtL4TGCHMoTdxgOIijnNkS7Cl-r2DJl3VTFXK1xnYyU46EPFHwUoy63yPavYxkUJ1RM-VZP5e962j0HD3hoTvnPA7-oDg4cDwrZlNdhoDuYG4xZkSiWbor8J2gHnxpo8yvKyShjiKFEhhf3vw2d8XgrpjgAM1iB6efQuMq5UPtbiyTAQRcoqOOE5gwW-x6aYJiiPxJDVuTSPv7jzm7d3Ds7wV6pXWyEEtFu0_V_Q.vtshT8tpL4gkxtCHxqzZoJas7rCR-7B0d4FqXRDAdtY&dib_tag=se&keywords=36+inch+rear+axle+kit&nsdOptOutParam=true&qid=1728219795&sr=8-1 | .
Chassis metal tubing with protection | 6 x 1.5m | Not included yet - need assessor's decision | 105 | 115.36
2'x4' timber C24 Sawn treated | 3x3m (+ delivery) | 39.38 | https://fulhamtimber.co.uk/checkout
8" Bolts + nuts | x25 | 13.39 | https://www.fastco.co.uk/coach-bolts-m8-x-200mm-zinc-plated-with-nuts-pack-of-25.html?gad_source=1&gclid=CjwKCAiAzPy8BhBoEiwAbnM9OwKXxAxkFmxLlWusxNLkVeA1nNnrjy58zEfqvEjaniK_l7NG2k72lhoC_IMQAvD_BwE | with delivery fee
2m x 3m Tarpaulin | To cover gokart outside while building | 6.99
Riding helmet |  | 12.99 | Decathlon
paint/protection
angle brackets | x12 | 26.7 | https://www.diy.com/departments/zinc-plated-mild-steel-angle-bracket-h-38mm-w-29mm-l-29mm-pack-of-2/243276_BQ.prd?storeId=1037&gStoreCode=1037&gQT=1
screws 40mm | 1 box | 9.89 | https://www.ebay.co.uk/itm/193895326954?_skw=box+of+stainless+screws&itmmeta=01JK43EJYTKCWYH446SKWR129J&hash=item2d250fe4ea:g:qI4AAOSwLc9fQrRa&itmprp=enc%3AAQAJAAAA8HoV3kP08IDx%2BKZ9MfhVJKnMxcHPZ5XoBBk4ZmoWEuRQhwPGUiGCcZDRpXG4pGWc8G59UboK5ArjRh%2BaOFqASnu097it--bGfNJA4XSHMgZWy18O2sGi1zKrz0JEKBZv0kN5kJhkmajDW%2B%2BIzwTWuwCdvKL4hxnHO9uhADBI8Q%2FYJ6KIIc47iIxszIURPUVzCvQadzb29LStzIXePdbW1jyvSMIsCXJSkf%2F4YHZXuGaWw6JkCUIce19nsvKcfvZxuCFeXWQa9G6dNI3C%2BDByX%2FF5j8M%2FcdmH%2BxQn6RXx8shuP2jFjOcSH44SwBqZ6HYJAg%3D%3D%7Ctkp%3ABk9SR86vuoOZZQ
washers AMZN | x20 | 5.99
handlebars | x2
throttle cable | 180cm | 6.7
Total |  | 361.29
Left for Bolts/Nuts/Washers |  | 138.71
Rod for wheels | 16mm | At school
Bolts 8" | x25 | 25
90* angle brackets | x18 | 25
screws 30mm ish | x50 | 75
washers | 20
https://www.diy.com/departments/diall-m10-carbon-steel-medium-flat-washer-dia-10mm-pack-of-20/3663602753605_BQ.prd
ask mr palmisano for angle brackets and screws
ask building services for 8" bolts
ask mr palmisano for washers

## Model 4.2 - Post Approval
Item Description | Dimensions | Cost £s (w/out discounts) | Link | .
6.5HP OHV Engine | 36 x 31 x 24cm | 71.99 | https://www.amazon.co.uk/Replacement-Minimal-Vibration-Consumption-Environments/dp/B0DLWRF399/ref=sr_1_1_sspa?crid=268Q96SOXSXRV&dib=eyJ2IjoiMSJ9.1xRgv8wtUAaE6GgyALSug4p35lOwX7x4T-Dw6LDXQHSQzU_7Calzcb7hKAm6SE8JVbJl8b6xZ-A6SZVA0B6fyzmNGL95u5eBLA0RqDUV-kCKV4gISNU4ZGG56vzwzMzzP2T_xaF5vMaqsi7-fqpKJldtHCSDlKhtoZsNMWDYtqq01pUANsPnrh5uHVWsR3IzQQaRoy8Ns2dStBeRj1CdaqUtPxF6sTKIKPLYJT_TnuIotu5bzhWV1jMptBLwDSu99z_UwDWLM4iOdkTz09MsP_ZyTp0xHmplOQOcL8iJlP8.5KdVx4LvsD3l5hlHrt46C7Ua56e3DQp209CbJrSeQLA&dib_tag=se&keywords=6.5hp+engine&qid=1742126584&refinements=p_36%3A5600-8000&rnid=388997011&sprefix=6.5HP+%2Caps%2C128&sr=8-1-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9hdGY&psc=1 | https://www.amazon.co.uk/Ejoyous-Replacement-Industrial-Agricultural-Air-Cooled/dp/B08VDQGQ27/ref=sr_1_5?dib=eyJ2IjoiMSJ9.fcwco9gx_NJeJrqLN_ejJzktR_G-f0qoU3bGH5i9seVFZ2ste6iZGOQTx0Kjy0fnp64jkD8NZ9BZYrDXaNFVswHK_SJmlRScM4KSGqjKaDH-RXHidWqfCMvH9spU7W1Wa82TKVmsNO3S7-BuGQSQTiz1z5uF4DjBWriEAHqPft_PSOCFWipIKsYUSNImD_-fxaG1iT9_Jrm3ZeMu9bc9Gp-bEIwLMKm4hAL-jIzWClI.QcyiH1B1XjjBzNuCx__dSvYZZBt-Ws969OAY2AzWnCg&dib_tag=se&keywords=6.5hp+engine&qid=1738700015&sr=8-5 | .
2x Front Wheels | 25 x 7.5cm | 10.95 | https://www.amazon.co.uk/ZENO-Pneumatic-Wheelbarrow-Puncture-Replacement/dp/B0BBGB2XVX/ref=sxin_15_pa_sp_search_thematic_sspa?content-id=amzn1.sym.ef88c0ed-6e25-412d-9436-2578b3d9875e%3Aamzn1.sym.ef88c0ed-6e25-412d-9436-2578b3d9875e&crid=15CI4FUJTMW0H&cv_ct_cx=wheelbarrow+wheel&keywords=wheelbarrow+wheel&pd_rd_i=B0BBGB2XVX&pd_rd_r=994d4314-c0a0-4258-a785-5f7697fa8c1d&pd_rd_w=brVPp&pd_rd_wg=27Gum&pf_rd_p=ef88c0ed-6e25-412d-9436-2578b3d9875e&pf_rd_r=KHZNCH65TJDRMHDB0VT4&qid=1741809775&sbo=RZvfv%2F%2FHxDF%2BO5021pAnSA%3D%3D&sprefix=wheelb%2Caps%2C85&sr=1-4-ad3222ed-9545-4dc8-8dd8-6b2cb5278509-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9zZWFyY2hfdGhlbWF0aWM&psc=1 | 20.95 | https://www.amazon.co.uk/ZENO-Pneumatic-Wheelbarrow-Puncture-Replacement/dp/B0BBKXVZ4G/ref=sr_1_13_sspa?dib=eyJ2IjoiMSJ9.A3OOQI0_Zv-fo18qNzdqTmxP0r7wTFkRvhcTcSbwpBPvszur4SN1Q1apeLngrmvNcu7vUdwZsfugdFv7DMdo0gQuJxI1moLNRtHKMiri1hJS8MKFt2gp3L2R-5zekSb64ot14EGvSoIcmMjte0-bVNUt3yluLnT4ugRRzaeIkIhBUhFCJxYDYiLwd4JzYhxImPQ62vt91eZbMvs-I_U_wkl9rSDSAmiqyqgltgCXHRCB4m1mOrIih7_bnp8GJE8pVP_V2P79LMwAditg-lQFbkpDm9P-PYybokWQ2w34w_U.NpfzG7XFxJUR7-twmqepLcpjDf4bwQytvQa2rpCzBUE&dib_tag=se&keywords=go+kart+wheels&qid=1728220361&s=automotive&sr=1-13-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9tdGY&psc=1 | https://www.amazon.co.uk/dp/B0DJQRMKHH/ref=sspa_dk_detail_0?psc=1&pd_rd_i=B0DJQRMKHH&pd_rd_w=MmJJW&content-id=amzn1.sym.46187d6a-4306-4bc6-830c-7b2085e0e39f&pf_rd_p=46187d6a-4306-4bc6-830c-7b2085e0e39f&pf_rd_r=ZZVB4FYTXGAYA5ZTEK21&pd_rd_wg=yVqgD&pd_rd_r=18384dd0-1d6e-486c-ad9b-7e99c9ac4b8c&s=automotive&sp_csd=d2lkZ2V0TmFtZT1zcF9kZXRhaWw
2x Rear Wheels | 13in x 5in | 33.98
Clutch + #35 chain | 3/4" bore | 21.29 | https://www.amazon.co.uk/4inch-Centrifugal-Clutch-Tooth-Chain/dp/B07WGD2NXP/ref=sr_1_4?crid=3855PVNHCYGMP&dib=eyJ2IjoiMSJ9.T6ZOODuvqSRxiJFAkxrxRmYnbIc4VdZVw2MsBRP6-kKgLzDPLVbuMQCIWkcQ3k5ULOloPayW-zqtAKE1KKxIlvp30YpP09nj-GBQw1UC6A1WTyPQLRRRkhizgExn1bAmvskWHB0q93_Jf56LxFX4U7WKDtLs0IP_oWTKTiDiiuoJPJ4xApoz0MZjWlcS1541sCXiyfDzXvrFhxFxT4SK658QdHUSgvmW2V6i49NU9JoETXKkM22_UFb_iYUPCmNAPJ-og6fuf2dZfp-i9o-U_-5GhtohJXEuNrZKWmQsr_XNv_gamI09jzd0iu2CBpzx0bQOd77eDWzd3ZqR5el3RibbbQzHAH_GutZvOJYW832vR4m2hTD-hhR0mSeEfBnRhlRZQymvdBEmpAMGJqgMD16gspJ-R0ErZ0z3UoTEwK6Sic-S9BZg4j3rtZjacCsK.fkLP0YTfqnh1Jn0CUzEbzwTFaZLaMOv71OHLhNOZnK8&dib_tag=se&keywords=3%2F4+sprocket+clutch&qid=1743099436&s=industrial&sprefix=3%2F4+sprocket+clutch%2Cindustrial%2C72&sr=1-4-catcorr | Torque Converter kit |  | 36.59 | 33.23 | https://www.ebay.co.uk/itm/205128657932?_trkparms=amclksrc%3DITM%26aid%3D1110006%26algo%3DHOMESPLICE.SIM%26ao%3D1%26asc%3D280672%2C281315%2C281326%2C280571%26meid%3D186a944cd9784cf1a6b137a5c75fcfd1%26pid%3D101875%26rk%3D2%26rkt%3D4%26sd%3D204669662830%26itm%3D205128657932%26pmt%3D1%26noa%3D0%26pg%3D2332490%26algv%3DSimVIDwebV3WithCPCExpansionEmbeddingSearchQuerySemanticBroadMatchSingularityRecallReplaceKnnV4WithVectorDbNsOptHotPlRecall%26brand%3DVEVOR&_trksid=p2332490.c101875.m1851&itmprp=cksum%3A205128657932186a944cd9784cf1a6b137a5c75fcfd1%7Cenc%3AAQAKAAABYHKEKKNMUePryBh1zZl0qrjonWK6%252Bbjh8v6%252FxTRbw1Loxqx736BoO2V7ozv6W4xuOBJjwGhPLWk9lnRB2teM6PFgOrZGVcTwpTth7MW79p066SWQrB1VasW1Di58xl1RMBXsH%252BaNxpzil0t8bdqbPkgJlZgvtHVYNSkxo5xG%252Bq21uJ4ns5oIp0ta3NI6ZOVv22RmL5ZD86%252Fs3DP06JHUohRrLvoTlSPvpz0IFHkhiQAz4o%252FeuAjUk73y3tqLCMOhz7cM5h7re4x3yp8Xk2w2VjMSH5FoJe8NyU00QOcSiB56p9dnvhRmEd7W3HS3lZUHCzK%252FjP9tiLySBCuOh7xHb7HQnaLehOXntAZHAwbjDaSFb0AeUTskrRRhhiEMY5MWOvPc1IMf2zOoZL7CMYbX9k3as7Gk5hedGOPp4tyylPApZ%252Fkx1hUWZK2XGvM6XB9F7v4HuDpRM0MUGiM%252F9rwRvBM%253D%7Campid%3APL_CLK%7Cclp%3A2332490&itmmeta=01JN48DZH8QG5DKRW28M5HQEG8 | https://www.ebay.co.uk/itm/204669662830
Separate #35 rear gear to attach | 37.5mm bore, 232mm diameter | 17.39 | https://www.amazon.co.uk/Sprocket-Stable-Saving-Mounting-Maintenance/dp/B09XVNZZNQ/ref=sr_1_10?crid=3EDC6GP6S1FDU&dib=eyJ2IjoiMSJ9.nvlhycfck24I64AWkRJtosrKOBZOaIgll5HC3FRB9ks0cu0S1LwGQJLuq0Ldg3n8SiDHKJV6jjj3eDYvLBvxNBOYmWG55ZH_dQbPJV2EuodBvq3pYRHqM25Sj32kyjn2XUGGJFJD70kU3WiawPYMnQ4jaWrXUDf5RF9iM5IWbuhScFRr8nHKPNqqT9lfZANDan9Nu8sSO49rt5f5gPaIxrpHICIpj91BIgDuqZO-eGk83jOI3TH9zzwfXYlPOWIKF5P3e3Bn4WWC-LI7kpxNIHEhL0Jb3pXgN_VtmMHZ27ZTdn2JhI-A_swY8zCIuzb6iSz62iYK_k7OQY7Xtw6uIsCbGF8t1Y9oEpS2UIJ13R5oxwdDrGK2hxUG5Xh_JpQ60JloZ0zef_vAREGIVBijYb9saGnTWBhd5Z0EtiIjnV7sl88MGsqOG_Wn8SFMxhnU.Tm4RHnPb4bX9e2nwH-03_s7AhPSXIQIUVx948wFh-vI&dib_tag=se&keywords=%2335+rear+sprocket&qid=1743109152&sprefix=%2335+rear+sprocket%2Caps%2C54&sr=8-10
Rear Axle Kit +Brake | 29" | 93.5 | https://www.amazon.co.uk/SEBLAFF-Assembly-Shaft-Chain-Brake/dp/B0BP1V2691/ref=sr_1_2?crid=1X8SBGDQF1Y1T&dib=eyJ2IjoiMSJ9.wj6UGutKkZ0k5IEJRLekCff9LKgIihUaYjIiZ-Q6CESGgNG7i7H2VVMSHTndKo1-Jf5aVyxpx8Tw1IxHm_pXmNCulgkU1N9Q4P9YD66WjV3Z9hIqRZRkEjbT_4k8UpjpqPUwaP9Q4NHRF1k8NIItPEUdxKztwnflzZlk8MGzfLXtnaJG7RUT-_0AOy76FmZ3zY-3nILe0ll5dXT15SMwWO3-QeEecRI1Zu-UpJnmpTE.VL3K3_PCf_GOucnUItHBTSgRQoffLRBriD8PtP-DPFE&dib_tag=se&keywords=go+kart+rear+axle+kit&qid=1740679747&sprefix=rear+axle+ki%2Caps%2C95&sr=8-2 | https://www.amazon.co.uk/GXYWADY-Master-Cylinder-Replacement-Rebuild/dp/B0CH3CTZ4F/ref=sr_1_1?dib=eyJ2IjoiMSJ9.6JNiA91wPg11dpNu-uDXeXTu5H9Q8Hbqk42hSsmj9G-tYq6BM_3skaf8Lt_zgGMKdZXPtL4TGCHMoTdxgOIijnNkS7Cl-r2DJl3VTFXK1xnYyU46EPFHwUoy63yPavYxkUJ1RM-VZP5e962j0HD3hoTvnPA7-oDg4cDwrZlNdhoDuYG4xZkSiWbor8J2gHnxpo8yvKyShjiKFEhhf3vw2d8XgrpjgAM1iB6efQuMq5UPtbiyTAQRcoqOOE5gwW-x6aYJiiPxJDVuTSPv7jzm7d3Ds7wV6pXWyEEtFu0_V_Q.vtshT8tpL4gkxtCHxqzZoJas7rCR-7B0d4FqXRDAdtY&dib_tag=se&keywords=36+inch+rear+axle+kit&nsdOptOutParam=true&qid=1728219795&sr=8-1
Chassis metal tubing with protection | 6 x 1.5m | 0 | 105 | 115.36
2'x4' timber C24 Sawn treated | 3x3m (+ delivery) | 40.03 | https://fulhamtimber.co.uk/checkout
zinc plated carbon steel M10 180mm bolts | x50 - Collect in store - bermondsey | 27.49 | https://www.screwfix.com/p/easyfix-general-purpose-threaded-coach-bolts-carbon-steel-bright-zinc-plated-m10-x-180mm-50-pack/54709 | https://www.screwfix.com/p/easyfix-general-purpose-coach-bolts-carbon-steel-bright-zinc-plated-m8-x-130mm-50-pack/19959 | https://www.fastco.co.uk/coach-bolts-m8-x-200mm-zinc-plated-with-nuts-pack-of-25.html?gad_source=1&gclid=CjwKCAiAzPy8BhBoEiwAbnM9OwKXxAxkFmxLlWusxNLkVeA1nNnrjy58zEfqvEjaniK_l7NG2k72lhoC_IMQAvD_BwE
#35 Roller Chain - 5 Feet | 160 links, 5 feet long |  | 11.99 | https://www.amazon.co.uk/Aobbmok-Roller-Chain-Connecting-Replacements/dp/B079L6DQFF/ref=pd_day0fbt_thbs_d_sccl_1/259-3488854-4744615?pd_rd_w=jKCaj&content-id=amzn1.sym.aa5f0976-1480-46a8-ac3e-86a6a439835e&pf_rd_p=aa5f0976-1480-46a8-ac3e-86a6a439835e&pf_rd_r=HX0836965GSJCRFJ6KS3&pd_rd_wg=NJ9Jm&pd_rd_r=83db4dfe-48cc-42f2-b1ae-9c0e992baff9&pd_rd_i=B079L6DQFF&th=1
3m x 3m Tarpaulin | To cover gokart outside while building | 6.99 | https://www.amazon.co.uk/Waterproof-waterproof-tarpaulin-camping-painting/dp/B084G9DX33/ref=sr_1_15?crid=1T2Y1D7K1ZA31&dib=eyJ2IjoiMSJ9.RRehQBCu4zwShToIZrZHrxkzTH9fG6n3h28scCe_M5SPd2nRaAg3eAirXUxaz0KA8S_X4dKpzm7tVnKWKS1IV7UHv2w0_uy85s0BVqkeuavJw3St0HzsyM-HxAvcODlqJ62CPZTHEfs3jL0CSDm1H-YN2KDp_SE295tssA2CTGWKFfSaunchbb4W9j_gzPN2pUVCWFGCXUiWha-vkHCVbUWKmy_-0bmhYsFNL4ypGqAKBDxXN0cm9vusWPHVEFvS_qJPW5CY619ic5m_bC3a6HpGpGnaIstbyoYizGjEY-VSGzojlizQ5TiT4e-8xiSDS2OlNE17UxMYl5BAW6LpBEZ1oVXGh07iJPOQ74qkaeBEB7N31OOtJpaKh4nBRRWXF2eHJbVQYhPeuVdCTpacqPj1MznL94GBrfKCptDrlOcNn7MJo7lnGLk_09UAv2XX.x8qMRw7VhD9inegOy9eyD6E_newGbdoRWsglkElJtOg&dib_tag=se&keywords=tarpaulin+3m+x+3m&qid=1740679059&sprefix=tarpaulin+3m+x+3m%2Caps%2C92&sr=8-15
Riding helmet |  | 0 | 12.99 | Decathlon
paint/protection |  | 0
angle brackets | 90mm X 90mm X 60mm - 12 pack | 12.99 | https://www.amazon.co.uk/gp/product/B085QDNHW1/ref=ewc_pr_img_1?smid=A37TFEBGRT7K24&th=1
Spax T-Star Plus Flat CSK Wirox Coated - (65484) | 100 pack - 80mm | 0 | 13.99 | https://www.toolstation.com/spax-t-star-plus-flat-csk-wirox-coated/p88122?store=null&utm_source=googleshopping&utm_medium=feed&utm_campaign=googleshoppingfeed&gad_source=1&gclid=CjwKCAiA8Lu9BhA8EiwAag16b-WSUjFM7dOylUlzuXh97Sa-xgRMZSvUWi7RiHeIifI5VVOPfjylQxoC6LwQAvD_BwE | do we really need ss steel? are woodscrews enough??
5 x 80mm | 100 pack - 80mm | 6.71
washers M10 x 25-50PCS | x50 | 9.39 | https://www.amazon.co.uk/sourcing-map-Stainless-Factories-Construction/dp/B0DDX11MCF/ref=sr_1_4?crid=15F5UJ7U7GLS1&dib=eyJ2IjoiMSJ9.Iv-xfT64IPqG1dGr2NITjytpGGaqlXPRTPIqcXGGWenDLc_exVfdvCzLX25CP-nGnf_2kxPwTIDDKg_LOdoaN0IkwnI03TlhsEnJQiffhjH3KGCgFyhPyKL8SCQyBb2kW-K6yGE-rAQFZDFttRcM5YVB9ev0XWkv4uVN9_PNGvy7zBe75e4P2eaTsvemxJCXNVhmiX5aKx83N7ax4b_pbIAOQIMPiCPeAdyFRx8g8bgz1F9vHnEv2lOyb5VuJJ_-5y9LCx5aS1vJ9HsnRzAUgnVVG3LmHnOdEz1HSXsuSpNoPEJEEtFWf6NTwVtSm_E3IVKGXvjdnLsTSCGDffYpIN0K0Dx8Qh_zYjkBW4HBrTY.D9nkZ7-75davPgEN5RZ7NYR3UML9il1EQpJbi155tzA&dib_tag=se&keywords=m10%2Bbolt%2Bwashers%2B100pcs&qid=1740856305&s=industrial&sprefix=m10%2Bbolt%2Bwashers%2B100pcs%2Cindustrial%2C56&sr=1-4&th=1 | https://www.amazon.co.uk/M10-Washers-Stainless-Spacers-25-50PCS/dp/B0D8HWSD57/ref=sr_1_6?crid=1QJ4V9BDFV4B&dib=eyJ2IjoiMSJ9.Wv92pTyCxQQt2tJzGlWFHy80CJS0cVWpQyf5fnZfvaY-zZIXeVLPFKJGYQ8pLkUDins3cAph6Gmejep9akNmPkS3tIkT_8wny3zU8riS3BCostGAOulv1T036w0xytifV5fYjjZmuGyRpWyqJDZcZ8qWZIYnjrDaGX9teXLIs0EFODNBeIWV465oNHEOkuqOhWTTa4YIBfLCQ5nbLGaEX8Z313ZGuzBetcapkkkd3MaaStP7uZri8qG_8td6KmwiBiGDuvsZJb1WhRYyBSzdSNrYvGE3PFWzGE5Uw2aYV69vgeG8dTdoJ4qGAMXwp1_LlbYCwWviIzRcLHNCe2KLc7pH0Uz5LRGK1HXByctGpz4.iEZyg5x33gZof9mQ1yKxr-xiZTuv03Ed9mHhZDyhM2s&dib_tag=se&keywords=m10%2Bbolt%2Bwashers&qid=1740781872&s=industrial&sprefix=m10%2Bbolt%2Bwashers%2Cindustrial%2C65&sr=1-6&th=1 | https://www.amazon.co.uk/gp/product/B0D8FKB8HJ/ref=ewc_pr_img_1?smid=A23LPY0XMLU7QZ&th=1
handlebars | x2 | 0
throttle cable | 180cm | 6.99 | https://www.ebay.co.uk/itm/166542584938?chn=ps&_ul=GB&_trkparms=ispr%3D1&amdata=enc%3A1l7DuBbc9SmK8IHs61hV0pQ47&norover=1&mkevt=1&mkrid=710-134428-41853-0&mkcid=2&mkscid=101&itemid=166542584938&targetid=2360873003490&device=c&mktype=pla&googleloc=9044906&poi=&campaignid=21690875706&mkgroupid=169793746720&rlsatarget=pla-2360873003490&abcId=10027099&merchantid=115236306&gad_source=1&gclid=CjwKCAiA8Lu9BhA8EiwAag16b8FUNG5_zo0M1CzuSnZsN3YyqKe9evkqRqb0ZTJO5kC12IvQw7Kl5RoCeugQAvD_BwE
Face masks | x100 |  | 2.49 | https://www.amazon.co.uk/Abena-Type-Disposable-Face-Loops/dp/B08P35F6RH/ref=sr_1_8?dib=eyJ2IjoiMSJ9.L5xN-e2hGi8iM12q_pDz_-3_cmfrnhB9MxvOgO0VQXYpDXE3MDFveaYkQRMrfamtkPdQNoTUMFdPgAICbbmKCznuzlHLBXI0ji22oyBWCEKGW2R8tWZuE4zUeHcbuiSNw6zYdwDlX3hgUA9jLeoqvSKG8g_F-zeiD98tUmpl1EX3EEg2Li8K_ye1w6UbNHLu0t2cr5OZcBI3j_x4lbTy4SVzc5f_ecfgiwiJY8D6577qN9sGj9FdJ167zRGZCzc5usY_fG9UBP8G2iiSchBUpJ9CmDDZUJGcMJtuAqN53Oa7gv3VN6Cz4aq57bVb1GZTVnZ1YzNNtH_U5ahVXSKpg0L6ttEaRKfOSWXVPeCzJhbHHhiWqLYU2SKVtR5lZU-bygGve2UHRRaMypiyy4PNvOmLDuEupmuvBH_UYSX_pLOzoTZW8jc9J2qdXt1NieDH.KIz762eLoQpzNp26FM5sqyxq1VQs45O7T8eg9UUtXTA&dib_tag=se&keywords=surgical+mask&qid=1740856762&sr=8-8
Gloves | x50 pairs | 4.99 | https://www.amazon.co.uk/MediHands-Powder-Gloves-Disposable-Medium/dp/B07L5MYF5V/ref=sr_1_25_sspa?dib=eyJ2IjoiMSJ9.HBkem1QGlMoz6ZjJK2sr93dLGCjfdpb8WLYFzwRjGvvs7fhtxYJQk8ubcuNAEYWSt4uCgKLTakYRARSevDGzpoYaIc0aWIklTpgkj0RwARJnISdxTBrcfA79Tc_D7N5iTXtL9DbBd1BvbEAnutM89mYgMz1Rdb30M_rmM267__zjvSusZg2zBTknF8QQAbIIo4RfRyS1uOa1yOzVvR6oj1gZgH6FcNQHeTJbv9gWRnitMn5nQdZlRVAhYqGLcWxSCpMYr6G5UYbezode-uXMZg4kdHh2UKgpg6tQcA5yno4.2D2Gek5ZpYriwTerGB1HI4TySxmzowpiW3o6xTg0Sbk&dib_tag=se&keywords=disposable%2BGloves&qid=1740858307&refinements=p_36%3A300-1100&rnid=118657031&s=diy&sr=1-25-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9idGY&th=1 | https://www.amazon.co.uk/Disposable-Examination-Preparation-Cleaning-Multi-Purpose/dp/B0D4DZD4LM/ref=sr_1_4?crid=17FYM30G1826L&dib=eyJ2IjoiMSJ9.vOEczs2J6sL28CdBf1O_CnouRQ1-WMOAmX9LQAlrvfJ6glpvqV9JfO8N50quq73aS0yB5v9-xcDwedx0TiGyFfMbBcq1dQbNm6iKdcsBHVUGsk31JCf-xUmsXnNV0XNgMHsr03EedW5iI5iFvIdqZkjpHXS9mEhneEPSc_BXoyPaovShl1Vzk-AGq_YAufYe43IsEFlBWw0mNpmIQkDsXsabL--L01fstyWzs1FKcFYz_icD01BmXCxQm0fMPLyD8ZTgNQPL6_tirDQt5X-5Eku2jD4vuWcuC18UZ_APC9RWs6AN4K4_W9MtUSajm33XMdtztweeFi7VL5kF2OcMrX7cUO6df_KOm_Eu77uOYnM.a0S5E5pbffUttzFyqu2X70hJfIes2i5Gqx7r9XowAhM&dib_tag=se&keywords=gloves%2Bdisposable%2Bmedium&qid=1740856921&refinements=p_n_feature_two_browse-bin%3A28138565031%2Cp_36%3A300-800&rnid=118657031&s=diy&sprefix=gloves%2Caps%2C88&sr=1-4&th=1
Total |  | 364.68
Remainder |  | -4.68
Rod for wheels | 16mm | At school

## Model 4.3 (Dynamic) Expenses
Transactions | £££ |  |  | Description | Price | Status | Return Expenses | Refunded
MEF Payment | 360
Steel M10 180mm bolts | 27.49 | Aquired, in custody
Gloves | 4.99 | Aquired, in custody
_____Return Gloves | -4.99 | Kept for personal use
Rear axle kit | 93.5 | Aquired, in custody
Tarp, Angle Brackets, Chain, Washers | 42.36 | Aquired, in custody |  | Chain my be returned if it doesn't fit sprocket on torque converter (and the converter sprocket fits the axle kit chain)
2x Rear, 2x Front Wheels. 10.95, 28.88 | 39.83 | Aquired, in custody |  | 4x Wheels | 20.95 | RETURNED | 2.73 | 18.22
x3 - 2"x4" 3m C24 timber | 40.03 | Aquired, in custody
Engine | 72.99 | Aquired, in custody
Torque Converter | 33.23 | Aquired, in custody
_____Return Chain | -11.99 | Returned & Refunded
_____Return Torque Converter | -33.23 | Returnless Refunded
_____Refund 65% - Engine | -46.79 | Returnless Refunded
Clutch + Chain | 21.29 | Aquired, in custody |  | 21.29
Rear gear | 17.39 | Aquired, in custody
Amazon Prime Delivery for clutch, chain and gear | 4.99 |  |  | 4.99 | Paid by Afnan (As of now)
_____Return Clutch + Chain #35 | -21.29 | Returned & Refunded
_____Return Rear gear #35 | -17.39 | Returned & Refunded
420 chain | 12.99 | Aquired, in custody
420 rear sprocket | 8.7 | Aquired, in custody
1" bore #40/41 clutch | 22.99 | Aquired, in custody | Madlife Garage Go Kart Mini Bike Centrifugal Clutch 1"Bore#40 41 Chain 14T Tooth Heavy Duty-black For GX Engine 4 stroke Go Kart Buggy : Amazon.co.uk: Automotive
Amazon Prime Delivery for clutch, chain and gear | 4.99 |  |  | 4.99 | Paid by Afnan (As of now)
7/8" to 1" shaft adapter | 6.84 | Aquired, in custody | Just in case the 1" bore is sized >25.4mm, or needs to be fitted tight on the shaft - might be returned
3/4" to 1" shaft adapter | 4.03 | Aquired, in custody | Just in case the 1" bore is sized >25.4mm, or needs to be fitted tight on the shaft - might be returned
_____Return 3/4" to 1" shaft adapter | -4.03 | Returnless Refunded
KP003 pillow block bearing | 11.99 | Aquired, in custody
M6 80mm x6 bolts for front axle | 6.69 | Aquired, in custody
Postage,Packing for bearings & bolts | 2.49
M8 bolts for engine | 5.99 | Aquired, in custody
Split Pins for front axle | 4.79 | Returned & Refunded
Postage,Packing for pins & bolts - Prime click & collect (Collected by Sn) | 2.99
_____Return split pins | -4.79
Castrol 1L 10W 30 engine oil | 9.99 | Aquired, in custody
1" Bore Shaft Collar | 6.99 | Aquired, in custody
4pcs T-Bolt hose clamp | 4.99 | Aquired, in custody
SET OF 2 X CASTLE NUTS M15, after rear left castle nut came unscrewed and got lost in the football pitch | 4.99 |  | https://ebay.us/m/g0ABIp
_____Return castle nuts m15 | -4.99 | Returned & Refunded
M16 nuts screwfix | 7.69
_____Return castle nuts m16 | -7.69
Remainder | -11.04
|  |  | 11.99 | 17.39
6.69
5.33
4.79
28.8
To Do | Minutes needed | In sequence with group | DIagram
Tape keystock to shaft, then place clutch on | 3 | #Lunch
Take engine to building services at lunch for petrol & testing. | 20 | #Lunch
Move chassis, tyres, axle, bolts, drill bits etc into workshop | 5 | A1 | [B]-¦S¦-[N]----[N]-¦S¦-[N]-- Bolt head-sprocket-nut-{space}-nut-sprocket-nut
Drill 3rd, 4th hole into #35 sprocket | 8 | B1
Arrange sprockts properly - Put M8 bolts through sprocket & fit nuts on either side of each- Mark where to cut bolts | 5 | B2
Hacksaw 4 bolts | 15 | B3
Grindstone #25 sprocket | 7 | C1
Find & gather required drill bits to drill last 10mm hole | 2 | D1
Drill last 10mm hole into the frame | 8 | D2
Put axle through bearings, place bearings into place, place washers, place nuts, put on spacers, sprockets, brake discs etc, wheels, castle screws. (Must plan all the layout and placement of every component beforehand) | 5 | D3 & B4 OVERLAP
Place the gokart on the floor, then place the engine cross planks, then place the engine | 1 | E1
Place chain over rear sprocket and clutch, and make sure to decrease chain slack as much as possible (call sir over) | 6 | E2
Mark outline on side planks where to place cross planks (after finished varying the tension). Mark where to place the engine on the engine cross planks (the outline). Then mark where to bolt | 8 | E3
Place the seat on to check if there is enough space to sit. Sit down on it and move your legs about | 5 | E4
Bolt engine in place. Place the shaft bolt and other bolts in place WITH WASHERS. Place a thick, circular wooden "stopper" on the shaft-bolt then drive the shaft bolt in with nuts and washers | 6
76
15:05 to 15:23 (went after Jummah in Mellish, then had to wait for him to show-up after Ms. Walters called him)
15:23 to 16:30 {sat with Mr. Farr troubleshooting the replica, then discussing and analysing possible combinations of adapter, wrench-adapter, clutch, keyway shape and key; had to take apart clutch as well together. Sir took Amazon link of clutch, dimensions and picture of this and the engine to show a mechanic's workshop}

## 220525 Gnatt chart
To Do | Minutes needed | In sequence with group |  | DIagram
To explain all the wor | 6 | INITIAL |  | Tape keystock to shaft, then place clutch on | 3 | #Lunch
Move chassis, tyres, axle, bolts, drill bits etc into workshop | 5 | A1 |  | Loosen the throttle handle's nut slightly for it to spring back easily | 2 | #Lunch
Explain all the work that needs to be done, how things need to be done, who needs to do what, what we're aiming to get done for today |  |  |  | Take engine to building services at lunch for petrol & testing. | 20 | #Lunch
Drill 3rd, 4th hole into #35 sprocket | 8 | B1
Arrange sprockts properly - Put M8 bolts through sprocket & fit nuts on either side of each- Mark where to cut bolts | 5 | B2 |  | [B]-¦S¦-[N]----[N]-¦S¦-[N]-- Bolt head-sprocket-nut-{space}-nut-sprocket-nut
Hacksaw 4 bolts | 15 | B3
Grindstone #25 sprocket | 7 | C1
Find & gather required drill bits to drill last 10mm hole | 2 | D1
Drill last 10mm hole into the frame | 8 | D2
Put axle through bearings, place bearings into place, place washers, place nuts, put on spacers, sprockets, brake discs etc, wheels, castle screws. (Must plan all the layout and placement of every component beforehand) | 5 | D3 & B4 OVERLAP
Measure diameter, draw & cut on bandsaw: circular wooden stopper for clutch (with Sir) | 10 | E1
Place the gokart on the floor, then place the engine cross planks, then place the engine | 1 | F1 | All actions that share are common letter are in sequence. For example, A1 must be followed by A2, then A3. But processes in group A can occur parallel to processes in group B or C or so on.
Place chain over rear sprocket and clutch, and make sure to decrease chain slack as much as possible (call sir over) | 6 | F2 | B(1-3) & C are independent and can happen simultaneously. B3 and C1 need to finish before D3. B4 will happen simultaneously as D3
Mark outline on side planks where to place cross planks (after finished varying the tension). Mark where to place the engine on the engine cross planks (the outline). Then mark where to bolt | 8 | F3 | E1 has to occur before F1
Place the seat on to check if there is enough space to sit. Sit down on it and move your legs about | 5 | F4 | A1 has to occur before B, C, D, E, F, G
Bolt engine in place. Place the shaft bolt and other bolts in place WITH WASHERS. Place a thick, circular wooden "stopper" on the shaft-bolt then drive the shaft bolt in with nuts and washers | 6 | F5 | Group F will occur after groups A, B, C, D and E are finished. G occurs after F.
Test how well the rolling frame works as someone pushes someone else from the hack | 10 | G1 | There are 3 people, and each person can only work on a single group at a time. For example, Bob needs to work and finish Group D before moving onto a new group, and Alice needs to work on group B before moving onto another group.
Everyone must do group A together only. For all other groups, only one person can carry out the tasks in that group.
101

## Sheet1
Start Time,"End Time","Task Description","Duration (min)","Group","Assigned To"
3:10 PM,"3:16 PM","To explain all the work","6","INITIAL","Afnan, Ognian, Joseph"
3:16 PM,"3:21 PM","Move chassis, tyres, axle, bolts, drill bits etc into workshop","5","A1","Afnan, Ognian, Joseph"
3:21 PM,"3:29 PM","Drill 3rd, 4th hole into #35 sprocket","8","B1","Afnan"
3:21 PM,"3:28 PM","Grindstone #25 sprocket","7","C1","Joseph"
3:21 PM,"3:23 PM","Find & gather required drill bits to drill last 10mm hole","2","D1","Ognian"
3:23 PM,"3:31 PM","Drill last 10mm hole into the frame","8","D2","Ognian"
3:28 PM,"3:38 PM","Measure diameter, draw & cut on bandsaw: circular wooden stopper for clutch (with Sir)","10","E1","Joseph"
3:29 PM,"3:34 PM","Arrange sprockts properly - Put M8 bolts through sprocket & fit nuts on either side of each- Mark where to cut bolts","5","B2","Afnan"
3:34 PM,"3:49 PM","Hacksaw 4 bolts","15","B3","Afnan"
3:49 PM,"3:54 PM","Put axle through bearings, place bearings into place, place washers, place nuts, put on spacers, sprockets, brake discs etc, wheels, castle screws. (Must plan all the layout and placement of every component beforehand)","5","D3/B4","Afnan, Ognian"
3:54 PM,"3:55 PM","Place the gokart on the floor, then place the engine cross planks, then place the engine","1","F1","Afnan, Ognian, Joseph"
3:55 PM,"4:01 PM","Place chain over rear sprocket and clutch, and make sure to decrease chain slack as much as possible (call sir over)","6","F2","Afnan, Ognian, Joseph"
4:01 PM,"4:09 PM","Mark outline on side planks where to place cross planks (after finished varying the tension). Mark where to place the engine on the engine cross planks (the outline). Then mark where to bolt","8","F3","Afnan, Ognian (until 4:05), Joseph"
4:09 PM,"4:14 PM","Place the seat on to check if there is enough space to sit. Sit down on it and move your legs about","5","F4","Afnan, Joseph"
4:14 PM,"4:20 PM","Bolt engine in place. Place the shaft bolt and other bolts in place WITH WASHERS. Place a thick, circular wooden ""stopper"" on the shaft-bolt then drive the shaft bolt in with nuts and washers","6","F5","Afnan, Joseph"
4:20 PM,"4:30 PM","Test how well the rolling frame works as someone pushes someone else from the hack","10","G1","Joseph"

## Model 4.3 Leftover parts
Date | Item | No. Left | N. Original | N. Selling | Notes | Brand (if known) | Listed? | Cumulative Buy Value for select items listed | Cumulative Selling Evaluation for select items listed | Revenue | % Depriciation | % Loss
2025-07-19 | M10 washers | 60 | 100 | 60 | 40 kept aside or used on gokart | Amazon | eBay | 5.4 | 5 | 0 | 29.9745 | 100
2025-07-19 | M10 180mm bolts & nuts | 23 | 50 | 20 |  | Screwfix | eBay | 10.996 | 7.7 | 7.7 |  | #REF!
2025-07-19 | M10 studdings | 18 | 18 | 0 |  |  |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | 5mm x 4mm split pins | 5 | 5 | 5 | Intact; brand new | Amazon |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | bicycle inner tube | 1 | 1 | 0 | most of it left, to be used for gokart engine's shaft, requires regular maintenance changes | Kc Nguyen |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | handlebar right handle | 1 | 1 | 0 | taken out for to reduce confusion, keep for gokart | The Charity Bike Shop |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | #25 ish chain | 1 | 1 | 0 | came with rear axle, idk what to do with it | Amazon |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | bicycle brake cable | 1 | 1 | 0 | keep for gokart | The Charity Bike Shop |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | M8 nuts | 18 |  | 0 | most came from school, to be returned, one nut per bolt bought from Amazon |  |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | M8 bolt full length | 1 | 6 | 0 | check amazon for product dimensions, keep for gokart | Amazon |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | M8 bolts shortened | 4 | 4 | 0 | needs grinding, keep for future use or return to school | Amazon |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | M8 bolts from school | 4 | 4 | 0 | to be returned | School |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | M10 bolt shortened | 1 | 1 | 0 | keep for gokart | Screwfix |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | 16mm rod offcut | 1 | 1 | 0 | return to school's metal store | School |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | M6 80mm x3 bolts for front axle | 3 | 7 | 0 | keep for gokart | Amazon, School (1) |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | M6 nuts | 8 |  | 0 | some mine, some from school, got one per bolt bought | Amazon, School |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | 16mm pillow block bearing P003 | 2 | 4 | 2 | keep for gokart |  |  | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2025-07-19 | 3/4" to 1" shaft adapter with key | 1 | 1 | 1 | Intact; brand new | Amazon |  | 4.03 | 4 | 0 | 0.74442 | 100
2025-07-30 | Torque Converter | 1 | 1 | 1 | Intact; brand new | Amazon | eBay | 33.23 | 27.99 | 7.7 | 15.7689 | 76.8282
| Total Grant | 360
| Total Left Over Buy Value | 48.256
| Total Left Over Listed Value | 39.69
| Total Left Over Sell Revenue | 7.7
| Total from grant effectively utilised | 351.434
| Percentage utilised effectively | 97.6206
| Average percentage depreciation | #DIV/0!
| Average percentage loss | #REF!

## Maintenance logs
2025-07-19 | #25-#35 rear sprocket screws need to be tightened and glued
2025-07-19 | rear right wheel needs to be bolted and double nutted per bolt
2025-07-19 | handlebars need to be double bolted
2025-07-19 | t bolt clamp on engine shaft needs to be tightened
2025-07-19 | washers need to be used for the engine support cross planks
2025-07-19 | double nut each bolt on front axle pillow bearing
2025-07-19 | Double nut bolt on either end of front axle preventing wheel sliding out
2025-07-19 | Need to add brake fluid, the put in the brake cylinder assembly